## Initial Plan
Color Coding |  | Completed |  |  |  | FALL 2020 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2020-08-25 | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | ALL | 2020-08-25 | 2020-08-29 | 100%
| Confirm Project Team Roles | ALL | 2020-08-25 | 2020-08-29 | 100%
| Develop two business cases | Nikhil, Sanket | 2020-08-25 | 2020-08-29 | 100%
| Develop Project Initiation Document (PID) | ALL | 2020-09-02 | 2020-09-13 | 46%
| Produce initial Project Plan, RACI | Ishaan, Katie | 2020-09-02 | 2020-09-15 | 25%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Katie | 2020-09-15 | 2020-09-19 | 100%
| Produce Context Diagram, Define System Interfaces | Ishaan | 2020-09-15 | 2020-09-19 | 100%
| Define Business Requirements | Katie | 2020-09-15 | TBD | 70%
| Agree to System Requirements types | Ishaan | 2020-09-15 | TBD | 40%
| Define Functional Decomposition | Ishaan | 2020-09-22 | 2020-09-26 | 0%
| Produce RCT document | Ishaan | 2020-09-22 | 2020-09-26 | 0%
| Decide which features to implement this semester | Nikhil | 2020-09-15 | TBD | 80%
| Produce analysis diagrams (UML, DFD) | Ishaan | 2020-09-29 | 2020-10-03 | 0%
| Define functional requirements (User Stories) | Ishaan | 2020-09-29 | 2020-10-03 | 0%
| Update Project Plan with additional requirements tasks | Sanket | 2020-10-29 | 2020-10-03 | 0%
MILESTONE 2: REQUIREMENTS IN PROGRESS
Design | Architecture design (2 diagrams) | TBD | TBD | TBD | 0%
| Database Design (ERD, Table spec) | Adam | 2020-10-13 | 2020-10-17 | 0%
| System Interface Design | TBD | TBD | TBD | 0%
| User interface design | TBD | TBD | TBD | 0%
MILESTONE 3: DESIGN IN PROGRESS
Code | GUI & Functionality Detailed Design | TBD | TBD | TBD | 0%
| Coding & Implemenation | TBD | TBD | TBD | 0%
MILESTONE 4: CODING IN PROGRESS
Integration & Testing | Plan testing, produce a Test Plan document | Athauda | 2020-11-03 | 2020-11-07 | 0%
| Evaluate Features to be Tested | Athauda | 2020-11-03 | 2020-11-07 | 0%
| Design Test Cases | Athauda | 2020-11-03 | 2020-11-07 | 0%
| Execute Test Cases | Athauda | 2020-11-03 | 2020-11-07 | 0%
| Anaylze Test Results | ALL | TBD | TBD | 0%
MILESTONE 5: TESTING IN PROGRESS
Project Presentation | Prepare Application Demo for the Presentation | ALL | TBD | TBD | 0%